"Pre-Production Activities"
=======================================================

Here is a quick reference pre-production activity list for directors.

PRE-PRODUCTION ACTIVITIES

1) Location Scouts

- the location manager has a concept meeting with the producers and the director after 
reading the script
- the location manager finds as many choices as possible for the Director
- (always try and group as many locations together as possible)
- scouts: Director/Location Manager/1st AD/Producer/PM or UPM/Art Director/Transportation Co-ord or a Driver

First Scouts (when their is lots of time!) 
- does it work for the Director 
- does it work for the schedule

Last Scouts (when their is no time left!) 
- does it work for the schedule 
- does it work for the director

2) Department Head Meetings

The director should have the following meetings: 
- concept meeting with producers/location manager/art director 
- script meeting with producers and writer (if available) 
- casting meeting with producers and casting director 
- costumes 
- props 
- set dec 
- special FX 
- stunts 
- extra casting 
- transportation 
- other (animals,optical FX) 
- visit the set and talk to - DOP/hair & make up/sound/actors

3) Director/1st AD Meeting

- go through the script scene-by-scene 
- give the AD a list of all special equipment needed
(crane, steadicam, circle track, special lenses, insert car etc.) 
- find out what he thinks/what he says/what he wants

4) Production Co-Ordinator

- consult them regarding your travel, hotel arrangements, family travel etc.

5) Production Manager

- go over all concerns with PM (budget etc) 
- prep is the time to organize (make mistakes on paper) 
- go in prepared and speak your mind ("CYA"!) 
- let them know if you foresee a problem early (overtime etc.)

6) Extra Casting Meeting/Budget

- 1AD, 2AD, Extra Casting, Costume Designer go over the extra's for the show

7) Stunts and Special FX

- get to know the Stunt Co-ordinator and SPFX Co-ordinator 
- (the 1AD is the on-set Safety Supervisor-Safety Meetings) 
- go over all details of a stunt or special FX so you know the 
potential dangers, length of time for shooting and other details

8) Animals

- talk to the trainers about the animals and the script 
- take time to watch them rehearse the animals 
- find out the animal's specific feeding times, work times habits

9) Children

- scheduling is more difficult with children under age 16 
- get to know the parents, guardians and tutors 
- always be honest with parents and tutors. Let them know what is really going on regarding time etc.

10) Day-Out-Of-Days(DOD)

- this shows you the work, travel, hold days for all actors

11) One Liner 
- sets the schedule out on a "one line" basis for quick reference (usually on Movie Magic)

12) Key Location Survey

- Director, 1AD, 2AD, PM, LM, ALM, Producer, Set Dec, Art Director, DOP, Grip, Gaffer, 
Transportation Captain, Construction Co-ord, Sound

13) Production Meeting

- review of all production arrangements and the director's concepts 
- the AD reads through the script scene-by-scene (no dialogue) and not by the one-liner 
- every department discusses with the director their specific requirements 
- it is an open discussion about the show 
- it is usually the last time anything can be asked for by the director (re: budget)

14) The Shooting Schedule (1AD)

- the show information (individual elements) is put into breakdown pages for distribution to crew

15) Stock Shots, Second Unit, Video Playback, Photographs, Inserts

- these items have a tendency to be forgotten. Make sure the AD has noted them